## Hours Log
RINA Internship Work Hour Log – PRT604
Internship start date | 2026-04-04 |  |  | Total logged hours | 140.5
Required PRT604 hours | 270 |  |  | Remaining hours | 129.5
Milestone length | 4 weeks each |  |  | % of required hours | 52.04%
Milestone coverage | 4 milestones / 16 weeks |  |  | Current milestone | Milestone 3
Important note | Milestone totals must match the final Unit report. |  |  | Latest logged date | 2026-06-17
Date | Week | Milestone | Work activity / evidence | Hours | Cumulative hours | Remaining hours
2026-04-10 | Week 1 | Milestone 1 | Initial meeting with Prof. Stephen about internship scope | 1 | 1 | 269
2026-04-10 | Week 1 | Milestone 1 | Home reading: reviewed internship brief and noted project scope/evidence requirements | 2.5 | 3.5 | 266.5
2026-04-17 | Week 2 | Milestone 1 | Industry meeting with Lyndal Hugo about Orlar and project scope | 1 | 4.5 | 265.5
2026-04-17 | Week 2 | Milestone 1 | Home reading: reviewed Orlar background and germination trial notes | 3 | 7.5 | 262.5
2026-04-23 | Week 3 | Milestone 1 | Meeting with Prof. Stephen about work process and planning | 1 | 8.5 | 261.5
2026-04-24 | Week 3 | Milestone 1 | Home preparation: reviewed planned work process and organised notes/hours/evidence | 2.5 | 11 | 259
2026-04-29 | Week 4 | Milestone 1 | Meeting with group members about work process | 1 | 12 | 258
2026-04-30 | Week 4 | Milestone 1 | Home preparation: reviewed basic image-capture materials and notes for upcoming training | 3 | 15 | 255
2026-05-01 | Week 4 | Milestone 1 | Meeting with Prof. Stephen | 1 | 16 | 254
2026-05-06 | Week 5 | Milestone 2 | Meeting with Pablo about drone instructions and image capture / understanding the image-processing workflow | 1 | 17 | 253
2026-05-07 | Week 5 | Milestone 2 | Organised drone image files and reviewed the DJI naming convention and band labels | 4 | 21 | 249
2026-05-08 | Week 5 | Milestone 2 | Extracted and checked sample drone image sets; compared RGB and false-colour preview images | 3 | 24 | 246
2026-05-08 | Week 5 | Milestone 2 | Read notes on multispectral bands and vegetation indices relevant to Mavic 3M images | 4 | 28 | 242
2026-05-10 | Week 6 | Milestone 2 | Wrote an initial Python exercise to parse DJI filenames and group images by timestamp and image number | 6 | 34 | 236
2026-05-11 | Week 6 | Milestone 2 | Meeting with Prof. Stephen | 1 | 35 | 235
2026-05-11 | Week 6 | Milestone 2 | Practised loading TIF multispectral bands and checking image dimensions and metadata | 5 | 40 | 230
2026-05-12 | Week 6 | Milestone 2 | Created a basic RGB, Green, Red, Red Edge and NIR comparison figure for a sample image set | 4 | 44 | 226
2026-05-14 | Week 6 | Milestone 2 | Drafted simple notes on why the F preview image should not be used for quantitative analysis | 3 | 47 | 223
2026-05-16 | Week 7 | Milestone 2 | Implemented a sample NDVI calculation using the NIR and Red bands | 6 | 53 | 217
2026-05-17 | Week 7 | Milestone 2 | Implemented a sample NDRE calculation using the NIR and Red Edge bands | 5 | 58 | 212
2026-05-18 | Week 7 | Milestone 2 | Tested simple vegetation-mask thresholds and reviewed false positives | 6 | 64 | 206
2026-05-19 | Week 7 | Milestone 2 | Meeting with group members to discuss the image-processing workflow and next steps | 1 | 65 | 205
2026-05-20 | Week 7 | Milestone 2 | Calculated basic vegetation-pixel / canopy-cover percentage for sample images | 4 | 69 | 201
2026-05-23 | Week 8 | Milestone 2 | Organised code/notebook outputs and screenshots for internship evidence | 5 | 74 | 196
2026-05-24 | Week 8 | Milestone 2 | Prepared Milestone 2 bullet points and weekly checkpoint notes | 4 | 78 | 192
2026-05-25 | Week 8 | Milestone 2 | Reviewed limitations of the test images and noted next steps for the germination-tray workflow | 4 | 82 | 188
2026-05-26 | Week 8 | Milestone 2 | Cleaned folders and updated the timesheet and evidence records | 5 | 87 | 183
2026-05-29 | Week 8 | Milestone 2 | Consolidated total hours and aligned the Milestone 2 report with the logbook | 3 | 90 | 180
2026-06-01 | Week 9 | Milestone 3 | Meeting with Prof. Stephen | 1.5 | 91.5 | 178.5
2026-06-02 | Week 9 | Milestone 3 | Group Meeting | 1 | 92.5 | 177.5
2026-06-08 | Week 10 | Milestone 3 | Fieldwork (Developing seedling base for trial) | 7 | 99.5 | 170.5
2026-06-09 | Week 10 | Milestone 3 | Fieldwork (Developing seedling base for trial) | 7 | 106.5 | 163.5
2026-06-10 | Week 10 | Milestone 3 | Mock trial: photographed Microbes and No Microbes trays and recorded treatment labels, capture condition and visual observations | 2.5 | 109 | 161
2026-06-10 | Week 10 | Milestone 3 | Organised first-trial RGB images into treatment folders; checked original pixel images and planned image-inventory outputs | 3 | 112 | 158
2026-06-11 | Week 10 | Milestone 3 | Python exercise: created image-inventory and treatment-labelling workflow for the first trial and reviewed metadata / real pixel-value needs | 5 | 117 | 153
2026-06-11 | Week 10 | Milestone 3 | Reading suggested by Prof. Stephen: reflectance, incoming light intensity, image condition/status and limitations of RGB photography | 3 | 120 | 150
2026-06-12 | Week 10 | Milestone 3 | Reading/practice: remote-sensing vegetation-index calculations, NDVI/NDRE concepts and why true indices need multispectral bands | 4.5 | 124.5 | 145.5
2026-06-13 | Week 11 | Milestone 3 | Fieldwork (First Trial) | 8 | 132.5 | 137.5
2026-06-15 | Week 11 | Milestone 3 | Meeting with Prof. Stephen | 1 | 133.5 | 136.5
2026-06-16 | Week 11 | Milestone 3 | Drone Setup/Trial Image Capture/Meeting with Prof. Stephen | 4 | 137.5 | 132.5
2026-06-17 | Week 11 | Milestone 3 | Drone Setup/Trial Image Capture | 3 | 140.5 | 129.5
2026-06-17 | Week 11 | Milestone 3 |  |  |  | 270
Reminder | For PRT604 submission, the Excel summary of work experience should be submitted with the PDF report, and the hour totals in milestone reports should match the final report.
How to use | Add each work session from row 9 onward. Enter only Date, Work activity, Hours, Category, Status and Notes. Week, Milestone, Cumulative Hours and Remaining Hours update automatically.
Milestone rule | Each milestone is treated as a 4-week block: M1 weeks 1–4, M2 weeks 5–8, M3 weeks 9–12, M4 weeks 13–16.

## Milestone Summary
RINA Internship Milestone Summary
Milestone | Week range | Start date | End date | Report/sign-off checkpoint | Suggested focus | Target hours | Actual hours | Progress vs target | Cumulative hours | Remaining to 270 | Status
Milestone 1 | Weeks 1-4 | 2026-04-04 | 2026-05-01 | End of Week 4; obtain supervisor signature | Orientation, protocol understanding, logging structure, initial meetings and trial planning. | 67.5 | 16 | 23.7% | 16 | 254 | Behind planning target
Milestone 2 | Weeks 5-8 | 2026-05-02 | 2026-05-29 | End of Week 8; obtain supervisor signature | Drone image review, DJI band/naming exercise, Python file grouping, basic multispectral indices, vegetation mask and evidence notes. | 67.5 | 74 | 109.6% | 90 | 180 | On track for milestone
Milestone 3 | Weeks 9-12 | 2026-05-30 | 2026-06-26 | End of Week 12; obtain supervisor signature | Growth metrics, germination analysis, data integration, visualisation and interim findings. | 67.5 | 45.5 | 67.41% | 135.5 | 134.5 | In progress
Milestone 4 | Weeks 13-16 | 2026-06-27 | 2026-07-24 | End of Week 16; obtain supervisor signature | Pipeline refinement, reproducibility, final evidence collation, final report alignment. | 67.5 | 0 | 0% | 135.5 | 134.5 | Not started
Key PRT604 requirement notes
Minimum work experience hours required | 270 hours
Minimum duration | 12 weeks or more if required
Consistency rule | Total hours claimed in milestone reports must match the final Unit report.

## Week Planner
RINA Internship 16-Week Planner by Milestone
Week | Start date | End date | Milestone | Suggested weekly focus | Planned hours | Actual hours | Cumulative hours | Notes
Week 1 | 2026-04-04 | 2026-04-10 | Milestone 1 | Confirm supervisor expectations, scope, safety, PRT604 logging and evidence requirements. | 16.88 | 3.5 | 3.5 | Initial meeting and orientation.
Week 2 | 2026-04-11 | 2026-04-17 | Milestone 1 | Review Orlar/RINA germination protocol; clarify treatment groups and data to collect. | 16.88 | 4 | 7.5 | Industry/project context meeting.
Week 3 | 2026-04-18 | 2026-04-24 | Milestone 1 | Design folder structure, image naming convention and raw data sheet format. | 16.88 | 3.5 | 11 | Follow-up meeting and planning.
Week 4 | 2026-04-25 | 2026-05-01 | Milestone 1 | Prepare Milestone 1 report; confirm early evidence and supervisor sign-off. | 16.88 | 5 | 16 | Group and supervisor meetings.
Week 5 | 2026-05-02 | 2026-05-08 | Milestone 2 | Support trial setup; define fixed camera position, lighting and capture timing. | 16.88 | 12 | 28 | Drone instruction, band naming review and file organisation.
Week 6 | 2026-05-09 | 2026-05-15 | Milestone 2 | Capture sample images; begin preprocessing, segmentation and feature extraction trials. | 16.88 | 19 | 47 | Python file grouping, band loading and comparison figure exercises.
Week 7 | 2026-05-16 | 2026-05-22 | Milestone 2 | Compare image-derived germination counts against manual observations. | 16.88 | 22 | 69 | NDVI, NDRE, vegetation mask and canopy-cover exercises.
Week 8 | 2026-05-23 | 2026-05-29 | Milestone 2 | Prepare Milestone 2 report; document pipeline status and issues. | 16.88 | 21 | 90 | Evidence organisation, milestone notes and logbook alignment.
Week 9 | 2026-05-30 | 2026-06-05 | Milestone 3 | Develop canopy cover, colour index and simple height-proxy metrics. | 16.88 | 2.5 | 92.5 | Supervisor and group meetings.
Week 10 | 2026-06-06 | 2026-06-12 | Milestone 3 | Mock trial setup, treatment image capture, RGB image workflow, reflectance/vegetation-index reading and evidence notes. | 16.88 | 43 | 135.5 | Field trial setup, mock-trial image capture, RGB image organisation, Prof Stephen reading topics and Milestone 3 evidence notes.
Week 11 | 2026-06-13 | 2026-06-19 | Milestone 3 | Build visualisations for germination, growth and treatment comparison. | 16.88 | 0 | 135.5
Week 12 | 2026-06-20 | 2026-06-26 | Milestone 3 | Prepare Milestone 3 report; summarize interim findings and evidence. | 16.88 | 0 | 135.5
Week 13 | 2026-06-27 | 2026-07-03 | Milestone 4 | Refine computer vision method and error handling for abnormal/stressed seedlings. | 16.88 | 0 | 135.5
Week 14 | 2026-07-04 | 2026-07-10 | Milestone 4 | Create reproducible scripts/notebook documentation and clean outputs. | 16.88 | 0 | 135.5
Week 15 | 2026-07-11 | 2026-07-17 | Milestone 4 | Draft final professional practice reflection using ICT/ACS competency framing. | 16.88 | 0 | 135.5
Week 16 | 2026-07-18 | 2026-07-24 | Milestone 4 | Complete Milestone 4/final check; reconcile all hours with final Unit report. | 16.88 | 0 | 135.5

## Source Notes
Source Notes / Requirements Used
Source | What it says / how it was used | Spreadsheet impact | Source link / file | Status
Unit Info- PRT604-2026- Masters of IT.pdf | PRT604 requires at least 270 hours of professional experience. Students must pass 12 weeks or more if required. Milestone reports are required, and the total hours claimed in Milestones must match the final Unit report. | Workbook tracks 270-hour target, weekly/milestone hours, and final consistency. | Uploaded PDF file | Used
Interdisciplinary Placement Ad RINA.docx | Internship includes controlled germination trials, structured image acquisition, computer vision for seedlings/growth/stress, sensor-data integration, automation, visualisation and documentation. | Weekly planner focuses on trial setup, image acquisition, CV/data pipeline and reporting. | Uploaded DOCX file | Used
LGH 240226 Germination Trials Singapore.docx | Protocol-style reference with 12 trays, daily seedling counts, height measurement, top-down photos, fixed capture setup and environmental data. | Supports image-capture and data-collection focus areas. | Uploaded DOCX file | Used
Gemini Google Doc | Helpful Gemini-generated internship information was linked by the user, but the browser view only showed a Google Docs page requiring JavaScript/sign-in and did not expose the document body. | Not used in formulas/content yet. Upload/export the doc as PDF/DOCX/TXT to incorporate it properly. | https://docs.google.com/document/d/13I5oMjiyUcV5M1231fY6c1mIlTHwlI1lBt_aEyujOiE/edit?usp=sharing | Pending content access
Prof Stephen suggested readings / image-analysis topics | Reflectance, incoming light intensity, generating reflectance-style images, suitable image condition/status, remote-sensing vegetation-index calculations, digital photography and real pixel values. | Supports Milestone 3 reading/logbook entries and the first-trial RGB image-analysis plan. | Supervisor guidance / user input | Used